## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Reset Password | Common |  | show label: ------If you've forgotten your password, enter your account and email---- allow registered user to input account name, email and Enter button. - Note that the default password send email to user is only available for a specific time duration as configured in the system config file. | Hiệp | Done | iter1 | iter2
2 | Create skill | Admin |  | Allow admin to add new skill include name of skill, default status is active and OK button. | Huy | Done | iter1 | iter2
3 | Update skill | Admin |  | Allow admin to update selected skill to update name of skill, choose status of skill in combobox and OK button. Skill has active/inactive status. | Huy | Done | iter1 | iter2
4 | Sign up | Public |  | Allow guest to input account name, email, password, confirm password, fullname, phone number, Date Of Birth, sex(male/female), address and Sign up button. After user click Sign up button, the Happy Programming system will send an email to require the user to confirm the info of account. | Hoang Anh | Done | iter1 | iter2
5 | View all skills | Public |  | Display all skills the Happy Programming Academy can training. On the screen include STT, Skill name (order by skill name) | Hoang Anh | Done | iter2 | iter3
6 | View list all mentor | Admin |  | Has textbox and search button. Show the list mentor infor in table format include STT, ID, Fullname, accountname, profression, number of currently accepted request, percentage completed, rate star and the link(or button) to allow active/inactive mentor. Need paging this page. | Huy | Done | iter2 | iter3
7 | User Authorization | Common |  | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | Huy | Done | iter3
8 | Change Password | Common |  | show label: ------Please enter your user name and password------ allow registered user to input account name, old password, new password, confirm new password and Enter button. | Hiệp | Done | iter1 | iter2
9 | Statistic request by me | Mentee |  | Show statitstic list of request belong to Mentee. Title of page is "Statistic of requests" This page allow Mentee user to see statistic of all requests of his/her. Show the Title (subject) of request, Total of request, total hours of all request, total Mentor. | Hiệp | Done | iter3
10 | List request by me | Mentee |  | Show the list of request belong to Mentee. Title of page is List of requests" This page allow Mentee user to see all new requests of his/her. Show the Title (subject) of request, deadline date, deadline hour, desciption of request, skills selected on create request screen and the, Update, Delete button. | Hiệp | Done | iter3
11 | View list following Request | Mentor |  | Show the list of request may be one or more mentees following the Mentor. Title of page is List of following requests" This page allow the Mentor to see all the invited requests to his/her. Show the Title (subject) of request, deadline date, deadline hour, content of request, skill of the request and correnponding accept, reject button of the request . | Hiệp | Done | iter3
13 | View profile-cv of mentor | Public |  | System displays profile-cv of that mentor, including: fullname, account, avatar, job, introduction, rating star & comment, statistic rating of each skill, service, achievement. | Hiệp | Done | iter2
14 | View statistic request | Mentor |  | This is a pop-up screen which allow the mentor to see all about the request belong to him include the number of currently accepted request, nummber of currently invited request, number of canceled request, percentage of cancel request, percentage of completed request, rating star. | Khánh | Done | iter3
15 | Update Mentee profile | Mentee |  | This page allow Mentee update his profile include avatar (link avatar of mentee), account name, full name, date of birth, email (only show, not allow to change the email) , sex, addrees and OK button. | Hiệp | Done | iter2
16 | Create CV of mentor | Mentor |  | This page allow the Mentor user to declar the skills he can training the Mentee users. Title of page: "Update CV of mentor" account name, fullname, date of birth, email, sex, addrees, Profession, profession introduction, select skills(checkbox), service description, archivement descition, the programming (framework) the Mentor can training the Mentee and the OK button. | Khánh | Done | iter2
17 | Update CV of mentor | Mentor |  | This page allow the Mentor user to update the skills he can training the Mentee users. Title of page: "Update CV of mentor" Avatar (link avatar of mentor) account name, fullname, date of birth, email, sex, addrees, Profession, profession introduction, select skills(checkbox), service desciption, archivement description, the programming (framework) the Mentor can training the Mentee and the OK button. | Khánh | Done | iter2 | iter3
18 | Rate & comment mentor | Mentee |  | This page rate the star, comment text and OK button. | Hiệp | Done | iter2
19 | View list all request | Admin |  | This page show all request of all mentees. On this page has search text box, button search, combobox of request status to allow admin to choose and filter, choose start date, end date of request. The infor of the list of request include: STT, ID, accountname (who create request), title of request, status. When admin user click on the ID (link) of the request, the request deail page will display. Need paging this page. | Hiệp | Done | iter3
20 | View list of skills | Admin |  | This page show all the currently technical skills the Happy Programming Academy can service the mentee. The skill info include: STT, ID, Name of skill, status (link or button) allow to enable/disable skill, link (or button) allow to update skill. The + button to allow go to create skill to add new skill. | Huy | Done | iter2 | iter3
21 | Statistic of all mentee | Admin |  | This page show statistic of all Mentee include: Name of Mentee, accountname, Nummber of Mentee, Total hours of all request, Total of skills of all requests. Note: Group by and order by name of Mentee. | Huy | Done | iter3
22 | List Mentor suggestion (for Mentee) | Mentee |  | This page show the list of mentor mapping the skills created request. The page include: Full name of mentor, account name, rating star, the number of requests the Mentor currently has and the Invite, button to allow the Mentee user can invite the Mentor he want to get training service. | Hoàng Anh | Done | iter3
23 | Create request | Mentee |  | Title of page is "Create request" This page allow Mentee user to create new request to get support from Mentor. Allow Mentee input Title (subject) of request, deadline date, deadline hour, content o f request, select skills (at least one checkbox and max is three checkboxes) the programming language(framework) the Mentee want to learn and OK button. The request will has status: Open, Processing, Cancel, Closed | Hoàng Anh | Done | iter2 | iter3
24 | Update request | Mentee |  | Title of page is "Update request" This page allow Mentee user to update new request to get support training from Mentor. Allow Mentee input Title (subject) of request, deadline date, deadline hour, content o f request, select skills (at least one checkbox and max is three checkboxes) the programming language(framework) the Mentee want to learn and OK button. The request will has status: Open, Processing, Closed | Hoàng Anh | Done | iter3 | iter3
25 | Sign in | Public |  | Title of page: Happy Programming allow registered user to input account name, password, checkboss remember password, link to Sign up page, link to reset password page. | Hoàng Anh | Done | iter1 | iter3
26 | Home Page | Public |  |  | Khánh | Done

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Loc | Screen/Function Description | In Charge | Status | Estimate Effort (H) | Begin | Deadline | SRS | SDS | Notes
1 | Sign up | Public | 120 | Allow guest to input account name, email, password, confirm password, fullname, phone number, Date Of Birth, sex(male/female), address and Sign up button. After user click Sign up button, the Happy Programming system will send an email to require the user to confirm the info of account. | Hoàng Anh | Done | 2 ngày - 12 tiếng | 2024-09-16 | 2024-09-18 | Done | Done
2 | HomePage,Search | Public | 120 | Allow users to search Mentor, Skills. View top hiring mentor(fullname, avatar,..), comment, statistics | Khánh | Done | 1 ngày - 8 tiếng | 2024-09-18 | 2024-09-20 | Done | Done | Change Function Description
3 | Create CV of mentor | Mentor | 120 | This page allow the Mentor user to declar the skills he can training the Mentee users. Title of page: "Update CV of mentor" account name, fullname, date of birth, email, sex, addrees, Profession, profession introduction, select skills(checkbox), service description, archivement descition, the programming (framework) the Mentor can training the Mentee and the OK button. | Đạt | To Do | 6h | 2024-09-18 | 2024-09-20 | Done | Done | Quit Project
4 | Create skill | Admin | 60 | Allow admin to add new skill include name of skill, default status is active and OK button. | Huy | Done | 2 ngày - 12 tiếng | 2024-09-15 | 2024-09-17 | Done | Done
5 | Reset Password | Common | 120 | show label: ------If you've forgotten your password, enter your account and email---- allow registered user to input account name, email and Enter button. - Note that the default password send email to user is only available for a specific time duration as configured in the system config file. | Hiệp | Done | 2 ngày - 12 tiếng | 2024-09-18 | 2024-09-20 | Done | Done
6 | Sign in | Public | 60 | Title of page: Happy Programming allow registered user to input account name, password, checkboss remember password, link to Sign up page, link to reset password page. | Hoàng Anh | Done | 6h | 2024-09-18 | 2024-09-20 | Done | Done
3 | Update skill | Admin | 60 | Allow admin to update selected skill to update name of skill, choose status of skill in combobox and OK button. Skill has active/inactive status. | Huy | Done | 2 ngày - 12 tiếng | 2024-09-18 | 2024-09-19 | Done | Done
8 | View all skills | Public | 60 | Display all skills the Happy Programming Academy can training. On the screen include STT, Skill name (order by skill name) | Đạt | To Do | 2 ngày-12 tiếng | 2024-09-16 | 2024-09-18 | Done | Done | Quit Project
9 | Change Password | Common | 60 | show label: ------Please enter your user name and password------ allow registered user to input account name, old password, new password, confirm new password and Enter button. | Hiệp | Done | 2 ngày-12 tiếng | 2024-09-20 | 2024-09-22 | Done | Done
10 | Update CV of mentor | Mentor | 120 | This page allow the Mentor user to update the skills he can training the Mentee users. Title of page: "Update CV of mentor" Avatar (link avatar of mentor) account name, fullname, date of birth, email, sex, addrees, Profession, profession introduction, select skills(checkbox), service desciption, archivement description, the programming (framework) the Mentor can training the Mentee and the OK button. | Khánh | Done | 2 ngày - 12 tiếng | 2024-09-18 | 2024-09-20 | Done | Done | Cant change Username
900

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Loc | Screen/Function Description | In Charge | Status | Estimate Effort (H) | Begin | Deadline | SRS | SDS | Notes
1 | Create CV of mentor | Mentor | 120 | This page allow the Mentor user to declar the skills he can training the Mentee users. Title of page: "Update CV of mentor" account name, fullname, date of birth, email, sex, addrees, Profession, profession introduction, select skills(checkbox), service description, archivement descition, the programming (framework) the Mentor can training the Mentee and the OK button. | Khánh | Done | 6h | 2024-10-01 | 2024-10-04 | Done | Done | Update another verion = create new
2 | HomePage,Search | Public | 120 | Show course, top course, the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown rating information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking - Shown courses information includes its thumbnail, title, brief information; the user is redirected to the course details on his/her clicking | Khánh | Done | 2h | 2024-10-02 | 2024-10-05 | Done | Done
3 | View profile-cv of mentor | Public | 120 | System displays profile-cv of that mentor, including: fullname, account, avatar, job, introduction, rating star & comment, statistic rating of each skill, service, achievement. | Khánh | Done | 6h | 2024-10-04 | 2024-10-05 | Done | Done | Mentee rating1
4 | View all skills | Public | 120 | -Display all skills the Happy Programming Academy can training. On the screen include STT, Skill name (order by skill name) - On the screen show 3 the recent skill -User can see the skill detail include mentor have that skills, number of mentor have that skill - User can search skill by input name | Hoàng Anh | Done | 6h | 2024-10-01 | 2024-10-03 | Done | Done
5 | View list of skills | Admin | 120 | This page show all the currently technical skills the Happy Programming Academy can service the mentee. The skill info include: STT, ID, Name of skill, status (link or button) allow to enable/disable skill, link (or button) allow to update skill. The + button to allow go to create skill to add new skill. | Huy | Done | 12h | 2024-10-01 | 2024-10-02 | Done | Done
6 | View list all mentor | Admin | 240 | Has textbox and search button. Show the list mentor infor in table format include STT, ID, Fullname, accountname, profression, number of currently accepted request, percentage completed, rate star and the link(or button) to allow active/inactive mentor. Need paging this page. | Huy | Done | 18h | 2024-10-03 | 2024-10-05 | Done | Done
7 | Create request | Mentee | 180 | Title of page is "Create request" This page allow Mentee user to create new request to get support from Mentor. Allow Mentee input Title (subject) of request, deadline date, deadline hour, content of request, select skills (at least one checkbox and max is three checkboxes) the programming language(framework) the Mentee want to learn and OK button. The request will has status: Open, Processing, Cancel, Closed | Hoàng Anh | Done | 12h | 2024-10-03 | 2024-10-05 | Done | Done
8 | Update Mentee profile | Mentee | 60 | This page allow Mentee update his profile include avatar (link avatar of mentee), account name, full name, date of birth, email (only show, not allow to change the email) , sex, addrees and OK button. | Hiệp | Done | 12h | 2024-10-02 | 2024-10-04 | Done | Done
9 | Rate & comment mentor | Mentee | 60 | This page rate the star, comment text and OK button. | Hiệp | Done | 12h | 2024-10-05 | 2024-10-05 | Done | Done

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Loc | Screen/Function Description | In Charge | Status | Estimate Effort (H) | Begin | Deadline | SRS | SDS | Notes
1 | Statistic of all mentee | Admin | 60 | This page show statistic of all Mentee include: Name of Mentee, accountname, Nummber of Mentee, Total hours of all request, Total of skills of all requests. Note: Group by and order by name of Mentee. | Huy | Done | 6h | 2024-10-10 | 2024-10-11 | Done | Done
2 | View list all request | Admin | 240 | This page show all request of all mentees. On this page has search text box, button search, combobox of request status to allow admin to choose and filter, choose start date, end date of request. The infor of the list of request include: STT, ID, accountname (who create request), title of request, status. When admin user click on the ID (link) of the request, the request deail page will display. Need paging this page. | Huy | Done | 18h | 2024-10-12 | 2024-10-15 | Done | Done
3 | User Authorization | Common | 240 | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | Huy | Done | 18h | 2024-10-16 | 2024-10-17 | Done | Done
4 | Manager CV & Slot list | Manage | 240 | Show mentor cv & slot list, mentor profile detail include: id, Account Name, Avatar, Email, allow to set active or inactive cv & slot and only one cv of one mentor have cv active, feedbacks of mentee by mentor have search bar and popup view cv of mentor, mentor account name direct to profile-cv of that mentor | Khánh | Done | 6h | 2024-10-10 | 2024-10-12 | Done | Done
5 | Statistic request by me | Mentee | 60 | Show statitstic list of request belong to Mentee. Title of page is "Statistic of requests" This page allow Mentee user to see statistic of all requests of his/her. Show the Title (subject) of request, Total of request, total hours of all request, total Mentor. | Hiệp | Done | 16h | 2024-10-16 | 2024-10-18 | Done | Done | name = "StatisticRequestByMenteeSV", urlPatterns = {"/statisticrequestbymentee"}
6 | List request by me | Mentee | 120 | Show the list of request belong to Mentee. Title of page is List of requests" This page allow Mentee user to see all new requests of his/her. Show the Title (subject) of request, deadline date, deadline hour, desciption of request, skills selected on create request screen and the, Update, Delete button. | Hiệp | Done | 18h | 2024-10-12 | 2024-10-15 | Done | Done | name = "ListRequestByMenteeSV", urlPatterns = {"/listrequestbymentee"}
4 | Update request | Mentee | 180 | Title of page is "Update request" This page allow Mentee user to update new request to get support training from Mentor. Allow Mentee input Title (subject) of request, deadline date, deadline hour, content of request, select skill, select slots the programming language(framework) the Mentee want to learn and update button. | Hoàng Anh | Done | 12h | 2024-10-13 | 2024-10-14 | Done | Done
7 | List Mentor suggestion (for Mentee) | Mentee | 240 | old:This page show the list of mentor mapping the skills created request. The page include: Full name of mentor, account name, rating star, the number of requests the Mentor currently has and the Invite, button to allow the Mentee user can invite the Mentor he want to get training service. new:This page show the list of mentor with the most request .The page include: Full name of mentor, rating star, the number of requests the Mentor currently has, skill mentor has and the Invite button or view cv to allow the Mentee user can invite the Mentor he want to get training service, filter mentor by rate, price. | Hoàng Anh | Done | 12 | 2024-10-14 | 2024-10-16 | Done | Done
6 | List of inviting request | Mentor | 60 | Show the list of request may be one or more mentees invite the Mentor. Title of page is List of invited requests" This page allow the Mentor to see all the invited requests to his/her. Show the Title (subject) of request, deadline date, deadline hour, content of request, skill of the request and correnponding accept, reject button of the request . | Hiệp | Done | 18 | 2024-10-18 | 2024-10-20 | Done | Done | name = "ListRequestOfMentorSV", urlPatterns = {"/listrequestofmentor"}
8 | View statistic request | Mentor | 240 | This is a pop-up screen which allow the mentor to see all about the request belong to him include the number of currently accepted request, nummber of currently invited request, number of canceled request, percentage of cancel request, percentage of completed request, rating star. | Khánh | Done | 6h | 2024-10-13 | 2024-10-15 | Done | Done
| Manger payment request | Manager | 120 | This page display request list by status and help manager can control the flow of payment by changing the status button of request and also display payment detail | Khánh | Done | 6h | 2024-10-17 | 2024-10-17 | Done | Done
| CRUD Slot | Common | 120 | Show schedule by display slot of mentor and mentee and also display available slot of mentor in view profile-cv of mentor | Khánh | Done | 6h | 2024-10-15 | 2024-10-17 | Done | Done
| Create Payment using VNPAY | Mentee | 120 | This document outlines the requirements for a payment system that allows Mentees to input the amount they wish to charge, process payments using the VNPAY sandbox platform, and view their payment history. | Hoàng Anh | Done | 12 | 2024-10-16 | 2024-10-18 | Done | Done
| Dashboard Admin | Admin | 60 | This page display total mentor and mentee user, newest user, chart and 'Active' and 'Inactive' Mentor and Mentee account | Hiệp | Done | 12 | 2024-11-05 | 2024-11-06 | Done | Done
| Attendance Schedule | Mentor | 60 | Mentor can see their study schedule and check mentee attendance | Hiệp | Done | 12 | 2024-10-27 | 2024-10-28 | Done | Done